Warehouse Tent Assembly Plan

8 outdoor 20 ft x 20 ft party tents | factory-style crew plan

| Field | Detail |
| --- | --- |
| Prepared for | Jessica Huang / LeCrown Properties |
| Date | July 3, 2026 |
| Source instructions | OTL10026 6 m x 6 m PE party tent instruction sheet |
| Primary decision | Use a 3-worker active floater production line when possible. |

Critical safety gate Do not leave any raised tent unanchored. If the surface is concrete or asphalt, the included spike anchors are not enough; use sandbags, water barrels, or bolt-down anchors.

# Recommended Layout

Use a two-row by four-column grid. Minimum practical work zone is about 105 ft wide by 55 ft deep, allowing 5 ft between tents and a 5 ft service aisle between rows.

| Area | Layout / instruction |
| --- | --- |
| Row 1 | T1 - 5 ft - T2 - 5 ft - T3 - 5 ft - T4 |
| Service aisle | 5 ft clear aisle between rows |
| Row 2 | T5 - 5 ft - T6 - 5 ft - T7 - 5 ft - T8 |
| Orientation | Keep zippered ends facing the same operational direction, preferably toward the warehouse or main access path. |

# Parts Staging

Create eight labeled kit piles before assembly: T1, T2, T3, T4, T5, T6, T7, and T8. Count parts before raising frames.

| Part | Total needed for 8 tents |
| --- | --- |
| Roof cover | 8 |
| Legs | 64 |
| Sidewalls with windows | 48 |
| Endwalls with zippers | 16 |
| Long bungees | 736 |
| Short bungees | 208 |
| Thick leg pegs | 64 |
| Thin wall pegs | 288 |
| Spiral pegs | 32 |
| Ropes | 32 |

# Time Model

Clock time is how long the job takes onsite. Labor-hours are clock time multiplied by worker count. More workers only improve the job when each role has productive work and avoids repeated setup.

| Crew | Operating model | Clock time | Labor-hours | Use |
| --- | --- | --- | --- | --- |
| 3 workers | Active specialized production line | 6-7.5 hr | 18-22.5 | Best plan |
| 2 workers | Paired build cell | 9-12 hr | 18-24 | Practical with calm weather |
| 1 worker | Solo prep plus one-tent-at-a-time finish | 24-32 hr | 24-32 | Fallback only |

| 3-worker style | Clock time | Labor-hours | Effect |
| --- | --- | --- | --- |
| Active Worker 1 | 6-7.5 hr | 18-22.5 | Worker 1 is a floating third hand after layout and staging. |
| Passive lead/checker | 7.5-9.5 hr | 22.5-28.5 | Adds about 1.5-2 onsite hours because Workers 2 and 3 still carry most build tasks. |

# Three-Worker Specialized Production Line

Use this plan when the goal is to finish in one workday. Worker 1 is not supervisor-only; Worker 1 floats to the current bottleneck.

| Role | Duties |
| --- | --- |
| Worker 1 | Lead runner, bottleneck relief, and quality control. Marks layout, counts parts, stages next tent, pre-sorts hardware, checks quality, and joins active build tasks whenever staging is ahead. |
| Worker 2 | Frame and roof builder. Assembles roof pipes/connectors, installs reinforcement triangles, handles one side of roof covers, and leads one side of the lift. |
| Worker 3 | Frame, wall, and anchor builder. Mirrors frame assembly, handles the other roof-cover side, prepares legs/anchors, and starts walls while Worker 1 checks prior work. |

| Phase | Worker 1 primary duty | If finished early |
| --- | --- | --- |
| Layout | Mark grid, door direction, aisle, and clearances | Start unloading hardware containers |
| Staging | Build eight labeled hardware and anchor piles | Pre-place legs at each connector point |
| Frame build | Check joints and hand parts to Workers 2 and 3 | Assemble reinforcement triangles or join frame assembly |
| Roof covers | Control bungee sequence and balanced cover tension | Hold cover edge or feed bungees |
| Raising | Verify anchor stations are ready before lift | Become the third lift person |
| Anchoring | Anchor the tent just raised | Help start next lift only after anchors are secure |
| Walls | Inspect zippers, hems, and wall direction | Attach walls and lower bungees |
| Final check | Walk every tent for screws, anchors, ropes, hazards | Correct issues immediately |

| Time | Task |
| --- | --- |
| 08:00-08:30 | Layout; Workers 2-3 unload and sort frame parts |
| 08:30-09:05 | Build hardware piles and stage all footprints |
| 09:05-11:15 | Build roof frames and reinforcement triangles |
| 11:15-12:00 | Pull roof covers and attach initial balanced bungees |
| 12:00-12:30 | Break and weather check |
| 12:30-13:45 | Raise each tent and anchor immediately |
| 13:45-14:45 | Attach walls, zippered ends, and remaining bungees |
| 14:45-15:15 | Final inspection, cleanup, and correction pass |

# Two-Worker Paired Build Cell

Use this plan when two people must complete the installation without a dedicated runner. Both workers help with roof covers and raising; neither works solo during lift, cover tensioning, or anchoring.

Mark the full grid together, then split tasks.

Build four roof frames in Row 1, then four roof frames in Row 2.

Stop after every two frames for a connection and parts-count check.

Pull covers onto Row 1, attach balanced bungees, then repeat for Row 2.

Raise and anchor one tent at a time; do not raise a second tent until the first is anchored.

After every two raised tents, attach walls before moving too far ahead.

| Expected result | Details |
| --- | --- |
| Clock time | 9-12 hours |
| Labor-hours | 18-24 |
| Schedule | One long day or split over two days if weather or anchoring slows work |

# One-Worker Solo Fallback Plan

Use only if the site is calm, time pressure is low, and the worker is not expected to raise loose tents in wind. A second person is strongly recommended for lift and anchoring.

Mark all eight footprints and door orientation.

Count parts and build eight hardware piles.

Prepare anchor stations before any roof cover is lifted.

Finish T1 completely before starting the raising stage on T2.

For each tent: assemble frame flat, pull roof cover low, attach balanced bungees, raise only in calm conditions, anchor immediately, attach walls, inspect, then move on.

Stop work if wind makes the roof cover or frame unstable.

| Expected result | Details |
| --- | --- |
| Clock time | 24-32 hours |
| Labor-hours | 24-32 |
| Schedule | Three to four partial workdays; fallback only |

# Anchoring Plan

Confirm the surface before scheduling installation.

| Surface | Anchoring approach |
| --- | --- |
| Grass or dirt | Use thick pegs at legs, spiral pegs and ropes at four corners, and thin pegs to secure walls. Confirm ground is firm enough to hold pegs. |
| Concrete or asphalt | Do not rely on the included spike anchors. Use sandbags, water barrels, or bolt-down anchors. Anchor every leg and corner before leaving the tent standing. |

# Weather Gate

Do not raise tents in meaningful wind.

Stop if wind moves the roof cover while workers are holding it.

Stop if gusts make the frame unstable.

Stop if rain makes the surface slippery.

Stop if anchors cannot be installed immediately.

# Site Readiness Checklist

| Done | Readiness item |
| --- | --- |
| [ ] | Surface type confirmed |
| [ ] | Exact work zone measured |
| [ ] | Warehouse doors, traffic lanes, drains, exits, and fire lanes clear |
| [ ] | Tent orientation confirmed |
| [ ] | All eight kits onsite |
| [ ] | Parts counted |
| [ ] | Anchoring method onsite |
| [ ] | Crew size confirmed |
| [ ] | Weather window checked |
| [ ] | Basic tools and packaging cleanup bins available |

# Completion Checklist

| Done | Completion item |
| --- | --- |
| [ ] | All eight tents standing in the planned grid |
| [ ] | All legs seated and tightened |
| [ ] | Roof covers evenly tensioned |
| [ ] | Sidewalls and endwalls attached with seams facing inside |
| [ ] | Zippers open and close correctly |
| [ ] | Every tent anchored |
| [ ] | Ropes and pegs do not create avoidable trip hazards |
| [ ] | Warehouse access remains clear |
| [ ] | Packaging and loose hardware removed |